	Project ID
	PJ001222 LSUAM 

	Project Fiscal Year
	2025-2026

	College/Department/Unit
	Manship School of Mass Communication 

	Title of Project
	Manship Laboratories and Working Groups

	Name of Principle Implementor
	Fanny Ramirez

	Email
	ramirez1@lsu.edu

	Phone Number
	(225) 578-2160

	Is this project complete?
	No

	Is this account ready to be closed?
	No

	Amount Awarded
	$49,234.00

	Amount Spent
	$25,000.54

	Equipment
	Upgrading and expanding laboratory equipment

	Purpose
	Requesting Extension

	Benefits Demographics
	Requesting Extension

	Comments
	Requesting Extension

	Justification (if an extension is requested)
	Requesting an extension because one of the computers we requested is still on back order (MSI RTX 5090 -- PO currently on backorder for $4522.00) and one of the licenses we requested cannot be renewed until August (i motions module subscription --- PO we can't put in until August for $12,000). Once those two are completed the project will be complete and we can close out the project. 



