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	Is this account ready to be closed?
	No

	Amount Awarded
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	Purpose
	The purposes of this project are to purchase and install (1) a fully equipped growth chamber in Room 140 and (2) LED panels to the current shelfing in Room 161, both in Julian C. Miller, the Horticulture building, to provide the most current technologies in advanced environment control as a critical instructional instrument for undergraduate and graduate courses that involves production and management of high value vegetable and novel specialty crops. 

	Benefits Demographics
	As estimated from courses that can use these systems, at least 700 of total usages are expected from students registered for various areas of concentrations under SPESS, with additional usage by RNR, and AEEE.

	Comments
	The growth chamber has been ordered, and we are waiting on its delivery, possibly in another two weeks from today (6/30/2026). The light room is adapted from an older tissue culture lab and has been cleaned and measured for installation of new racks. The racks are being quoted from two suppliers and will be installed with lights before the fall semester begins. 

	Justification (if an extension is requested)
	This project had an original completion date of 6/30/2026. We are waiting on the delivery of the growth chamber and working on the light room racks/lights. We would like to request that the completion date to be extended to 08/31/2026, by which date the growth chamber should be delivered and installed and the light room should be ready for courses to use.



