	Project ID
	PJ001232

	Project Fiscal Year
	2025-2026

	College/Department/Unit
	LSU Libraries

	Title of Project
	Expanding the LSU Libraries Creator Space.

	Name of Principle Implementor
	Michael Stewart / (Gina Costello, Co-PI)

	Email
	gcoste1@lsu.edu

	Phone Number
	(225) 578-2217

	Is this project complete?
	No

	Is this account ready to be closed?
	No

	Amount Awarded
	$51,171

	Amount Spent
	$38,870

	Justification (if an extension is requested)
	As part of the ITS Centralization Project, Michael Stewart (PI) has moved to a position entirely outside the Libraries as of May 15, 2026. He will not have any involvement in this project after May 15. Another staff member will be helping Co-PI Gina Costello with the remaining grant work.

This personnel change will delay our ability to complete certain parts of the project, so we request a 1-semester extension. 

Along with the extension, we request that Co-PI Gina Costello be made the sole PI and that Michael Stewart be removed from the project. 



